## Cover Page
AI Course
Capstone Project
Work Breakdown Structure
For Students
ⓒ2021 SAMSUNG. All rights reserved.
Samsung Electronics Corporate Citizenship Office holds the copyright of this document.
This document is a literary property protected by copyright law so reprint and reproduction without permission are prohibited.
To use this document other than the curriculum of Samsung innovation Campus, you must receive written consent from copyright holder.
Samsung Innovation Campus

## WBS
Capstone Project Work Breakdown Structure (WBS)
Done
In-progress
Delayed
Today |  | 2022-10-12
Project Team Name |  | Dark_Web_Crusaders
Project Topic |  | Traffic Sign Recongition System Using CNN
Task |  |  | Start date | End date | Responsibility | Deliverable | Task Status | W1 |  |  |  |  | W2 |  |  |  |  | W3 |  |  |  |  | W4
[8 empty] | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20
[8 empty] | 2019-01-01 | 2019-01-02 | 2019-01-03 | 2019-01-04 | 2019-01-05 | 2019-01-06 | 2019-01-07 | 2019-01-08 | 2019-01-09 | 2019-01-10 | 2019-01-11 | 2019-01-12 | 2019-01-13 | 2019-01-14 | 2019-01-15 | 2019-01-16 | 2019-01-17 | 2019-01-18 | 2019-01-19 | 2019-01-20
1. Exploring Generalized Traffic Sign Dataset |  |  | 28/9/2022 | 28/9/2022 | Shamaem |  | Done | bar: 2019-01-01 to 2019-01-13
2. Data Acquisition and EDA |  |  | 2022-01-10 | 2022-03-10 | Shamaem |  | Done | bar: 2019-01-01 to 2019-01-12
| 2.1 Data Acquisition |  | 2022-01-10 | 2022-01-10 | Shamaem |  | Done | bar: 2019-01-01 to 2019-01-08
| 2.2 EDA |  | 2022-02-10 | 2022-03-10 | Shamaem |  | Done | bar: 2019-01-01 to 2019-01-06
3 Pre-Processing |  |  | 2022-04-10 | 2022-05-10 | Shamaem |  | Done
| 3,1 Normalization |  | 2022-04-10 | 2022-04-10 | Shamaem |  | Done
| 3.2 Data Augmentation |  | 2022-04-10 | 2022-04-10 | Shamaem |  | Done
| 3.3 EDA after pre-processing |  | 2022-05-10 | 2022-05-10 | Shamaem |  | Done
4 Model |  |  | 2022-06-10 | 2022-10-10 | Toheed |  | Done
| 4.1 Building The Model |  | 2022-06-10 | 2022-06-10 | Toheed |  | Done
| 4.2 Training The Model |  | 2022-07-10 | 2022-07-10 | Toheed |  | Done
| 4.3 Validating The Model |  | 2022-08-10 | 2022-08-10 | Toheed |  | Done
| 4.4 Testing and Evulation |  | 2022-09-10 | 2022-09-10 | Toheed |  | Done
| 4.5 Visulaizaton and Results |  | 2022-10-10 | 2022-10-10 | Toheed |  | Done
5 Building Interface |  |  | 2022-11-10 | 2022-12-10 | Shamaem /Toheed |  | Delayed